## Sprint 1 Backlog
Sprint Backlog – Smart-Attend App – Sprint 1 (MVP)
Sprint Duration: 2 Weeks
Sprint Goal: Deliver a working MVP with Login + Geo-fencing + Teacher Dashboard for user testing
Task ID | User Story | Role | Acceptance Criteria | Priority | Estimated Hours | Assignee | Status | Sprint
US01 | As a student, I want to login via university ID so I can access my profile. | Student | - Login screen with University ID and password fields - Successful login navigates to student dashboard - Error shown for invalid credentials - Session persists until logout | High | 4 | Developer A | To Do | Sprint 1
US02 | As a teacher, I want to view a real-time list of present students. | Teacher | - Dashboard shows live list of students marked present - List auto-updates every 30 seconds - Shows student name + timestamp of entry - Filterable by class/section | High | 6 | Developer B | To Do | Sprint 1
US03 | As a system, I want to detect if a student is within 10m of the classroom. | System | - GPS geo-fence radius set to 10 metres - Triggers attendance marking automatically when student enters zone - Works on Android and iOS - Handles GPS signal loss gracefully | High | 8 | Developer C | To Do | Sprint 1
US04 | As a student, I want a notification when my attendance is marked. | Student | - Push notification sent within 5 seconds of geo-fence trigger - Notification displays class name and timestamp - Works with app in foreground and background - Tapping notification opens attendance history | Medium | 3 | Developer A | To Do | Sprint 1
US05 | As an admin, I want to manually override attendance for technical errors. | Admin | - Admin panel lists students with unconfirmed attendance - Admin can toggle attendance status (Present/Absent) - Override action logs: admin ID + timestamp + reason - Overrides visible with audit trail in reports | Low | 4 | Developer B | To Do | Sprint 1
TOTALS |  |  |  | High: 3 items, Medium: 1 item, Low: 1 item | 25 Hours Total
Medium:1 item
Low: 1 item